## Sheet2
Client | Project | Project Phase | Task | Task Description | Details | 2018-12-13 | 2018-12-14 | 2018-12-15 | 2018-12-16 | 2018-12-17 | 2018-12-18 | 2018-12-19 | 2018-12-20 | 2018-12-21 | 2018-12-22 | 2018-12-23 | 2018-12-24 | 2018-12-25 | 2018-12-26 | 2018-12-27 | 2018-12-28 | 2018-12-29 | 2018-12-30 | 2018-12-31
ApoIO | UI Development | Go live | Bug fixing | working on the timerange wise graph generation issue #16:master dashoboard : date picker useless scrollbars #17: master dashboard : Timerange modification does not impact well all the timeseries UI Changes in Clients machine. | The Time series data has some issue to load the bulk data. finding solution to load huge data and proper display. the piwebapi query has some issue occured with loading. R & D for api call and updating the chart accordingly. Dependency on PI DATA. Waiting for data. Data get and started working on the same. | working on the timerange wise graph generation issue
ApoIO | UI Development | Go live | Bug fixing | working on the timerange wise graph generation issue #16:master dashoboard : date picker useless scrollbars #17: master dashboard : Timerange modification does not impact well all the timeseries UI Changes in Clients machine. | The Time series data has some issue to load the bulk data. finding solution to load huge data and proper display. the piwebapi query has some issue occured with loading. R & D for api call and updating the chart accordingly. Dependency on PI DATA. Waiting for data. Data get and started working on the same. |  | working on the timerange wise graph generation issue
ApoIO | UI Development | Go live | Support | working on the timerange wise graph generation issue #16:master dashoboard : date picker useless scrollbars #17: master dashboard : Timerange modification does not impact well all the timeseries UI Changes in Clients machine. | The Time series data has some issue to load the bulk data. finding solution to load huge data and proper display. the piwebapi query has some issue occured with loading. R & D for api call and updating the chart accordingly. Dependency on PI DATA. Waiting for data. Data get and started working on the same. |  |  | working on the timerange wise graph generation issue
<Select> | <Select> | <Select> | Support
<Select> | <Select> | <Select> | Support
<Select> | <Select> | <Select> | Support
<Select> | <Select> | <Select> | Support
<Select> | <Select> | <Select> | Support
<Select> | <Select> | <Select> | Support
<Select> | <Select> | <Select> | Support
<Select> | <Select> | <Select> | Support

## Sheet5
<Select> | <Select>
Site Survey | Support
Site Visit | AMC
Site Survey Document | Enhancement
Software and Hardware quotations | Development
Request for Quotations | Deployment
Proposal | Meeting/Concall
Technical Proposal | Internal Discussion
Commercial Proposal | R&D
Create Bill of Material | Bug fixing
Site Requirments | Self Learning
Kick OFF | Knowledge Sharing Session
FDS (Blue Print) Sign off
Hardware and Software Procurment
Hardware Supply
Networking
Hardware Supply to site
Server Rack Setup
Server Integration
OS and MS Office Installation
Firewall placement and Configuration
Network Switch placement and Configuration
Cable Laying
Wireless Outdoor Devices Placement and configuration
Wireless Indoor Devices Placement and configuration
VPN Configuration
PI Integration
PI Server installation and configuration
AF Server installation and configuration
PLC Integration
Interface installation
DCOM Setting
ICU Installation
PI Interface Installation
PI Interface configuration
OPC server installation
OPC Server configuration
PI Auto Backup
PI Development
PI Tag creation
PI Tag Validation
PI Vision Installation
PI Vision Configuration
PI Vision Screen development
AF Hierarchy development
AF tag mapping
AF analysis
PI AF EventFrames
Email Notifications
SMS Notifications
Report Development
Database server Installation
Database Design
Report server Configuration
Database client installation
Database integration
Report Development
Report Design
Unit Testing
Auto Backup
Auto scheduling of Reports
Auto scheduling of ETL
UAT
Portal Development
Architecture Design
Front End Design
Back End Development
Manual Form
Coding / Development
Report and Dashbaord hosting
Portal log in configuration
Deployment
Portal UAT
Mobile App Development
Web Service devlopment
Database design
SQL Server Connectivity
Database design
PI WebAPI configuration
SAP Connectivity
Layout Design
Layout Functionality Implementation
Android / Reactnative development
APP UAT
Playstore Hosting -*If Required | Support
Go live | AMC
Support | Enhancement
AMC | Development
Deployment
Meeting/Concall
Internal Discussion
R&D
Bug fixing
Self Learning
Knowledge Sharing Session

## Sheet3
<Select> | <Select>
JSW Port | Jaigarh PIMS
JSW Energy | Yard Management (Phase I & II)
JSW Steel | GOA PIMS
Adani Ports | Dharamtar PIMS
Adani Wilmar | EC Report
Tata Power | Vijaynagar
Tata Steel | Ratnagiri
UTCL | Barmer
AVTB | Baspa
Balco Aluminium | Karcham
Balco Power | Mobile App
Sterlite | Dolvi OSIsoft PI
Bentley | Gantry Optimization
Deepak Fetilizers | Mundra Port Mercury AMC
ApoIO | Dahej AMC
Hazira AMC
Dhamara AMC
Goa AMC
Upgrade
Mundta PLC to SAP Phase 1
Mundta PLC to SAP Phase 2
CGPL
Central PI Tata Power
TSMC – Schefferville
SAP Integration
UTCL Patliputra
Phase 2
Sharepoint AMC
OSIsoft PI AMC
Korba MES
Korba MES
Shendra New Glass Plant
Cairn AMC
Deepak Fetilizers
UI Development

## Sheet6
<Select>
JSW Port | Jaigarh PIMS
Yard Management (Phase I & II)
GOA PIMS
Dharamtar PIMS
EC Report
JSW Energy | Vijaynagar
Ratnagiri
Barmer
Baspa
Karcham
Mobile App
JSW Steel | Dolvi OSIsoft PI
Gantry Optimization
Adani Ports | Mundra Port Mercury AMC
Dahej AMC
Hazira AMC
Dhamara AMC
Goa AMC
Upgrade
Adani Wilmar | Mundta PLC to SAP Phase 1
Mundta PLC to SAP Phase 2
Tata Power | CGPL
Centreal
Tata Steel | TSMC – Schefferville
UTCL | SAP Integration
UTCL Patliputra
AVTB | Phase 2
Sharepoint AMC
OSIsoft PI AMC
Balco Aluminium | Korba MES
Balco Power | Korba MES
Sterlite | Shendra New Glass Plant
Bentley | Cairn AMC
Deepak Fetilizers | Deepak Fetilizers